AZURE MIGRATION PROGRAMME

End-to-End Implementation Plan

Phase-by-Phase Execution with PowerShell, Terraform, CI/CD & Azure DevOps

| Document Type Implementation Plan | Version 1.0 — Initial Release |
| --- | --- |
| Phases Covered 6 Phases — Discover through Operate | Audience Migration Engineers, DevOps, Cloud Architects |

Table of Contents

1.  Programme Overview & Toolchain Setup

This document provides a comprehensive, sprint-level implementation plan for a large-scale Azure Migration Programme. Every phase is elaborated with exact scripts (PowerShell, Python, Bash), Terraform HCL patterns, Azure DevOps YAML pipelines, and acceptance criteria. The plan maps directly to the Technical Reference Blueprint and is designed to be executed sequentially, with automation artefacts produced in each phase feeding the next.

1.1  Programme Architecture at a Glance

The programme is structured across six phases spanning approximately 24–36 weeks for a programme migrating 100–500 workloads. Each phase produces versioned artefacts committed to Azure Repos, tested through CI gates, and deployed via Azure DevOps pipelines.

| Phase | Task Area | Duration | Sprints | Key Output |
| --- | --- | --- | --- | --- |
| 1 | Discover & Assess | Weeks 1–4 | S1–S2 | Azure Migrate export, wave matrix, PowerShell inventory scripts |
| 2 | Design & Landing Zone | Weeks 5–10 | S3–S5 | Terraform Landing Zone modules, networking, identity, governance |
| 3 | Build & Automate | Weeks 11–16 | S6–S8 | CI/CD pipeline templates, module library, policy automation |
| 4 | Migrate & Execute | Weeks 17–24 | S9–S12 | Wave execution runbooks, cutover scripts, smoke test suites |
| 5 | Govern & Secure | Ongoing | S3–S12 | Policy initiatives, Defender config, FinOps dashboards |
| 6 | Operate & Optimise | Post-go-live | S13+ | SLO dashboards, DR pipelines, KT deliverables |

1.2  Pre-Programme Toolchain Bootstrap

Before Sprint 1, every workstation and build agent must have the following toolchain installed and validated. The bootstrap script below automates this for Windows build agents and developer machines.

Bootstrap Script — Windows (PowerShell)

PowerShell — 00-bootstrap-toolchain.ps1

#Requires -RunAsAdministrator # Azure Migration Programme — Toolchain Bootstrap # Run once on each engineer workstation and Azure DevOps self-hosted agent param( [string]$TerraformVersion = '1.8.3', [string]$TFLintVersion = '0.51.1', [string]$TFSecVersion = '1.28.4', [string]$CheckovVersion = '3.2.0' ) Set-StrictMode -Version Latest $ErrorActionPreference = "Stop" function Install-Choco { if (!(Get-Command choco -ErrorAction SilentlyContinue)) { Set-ExecutionPolicy Bypass -Scope Process -Force iex ((New-Object Net.WebClient).DownloadString("https://chocolatey.org/install.ps1")) } } function Install-Tool([string]$Name,[string]$ChocoId,[string]$Version='') { Write-Host "Installing $Name..." -ForegroundColor Cyan $args = if ($Version) { "--version=$Version" } else { "" } choco install $ChocoId -y $args --no-progress ¦ Out-Null } Install-Choco Install-Tool 'Azure CLI' 'azure-cli' Install-Tool 'Terraform' 'terraform' $TerraformVersion Install-Tool 'kubectl' 'kubernetes-cli' Install-Tool 'Helm' 'kubernetes-helm' Install-Tool 'Git' 'git' Install-Tool 'Python 3.11' 'python' '3.11.9' Install-Tool 'Node.js' 'nodejs' Install-Tool 'jq' 'jq' # Install tflint Write-Host "Installing tflint $TFLintVersion..." -ForegroundColor Cyan $url = "https://github.com/terraform-linters/tflint/releases/download/v$TFLintVersion/tflint_windows_amd64.zip" Invoke-WebRequest $url -OutFile '$env:TEMP\tflint.zip' Expand-Archive '$env:TEMP\tflint.zip' -DestinationPath 'C:\tools\tflint' -Force $env:PATH += ";C:\tools\tflint" # Install tfsec Write-Host "Installing tfsec $TFSecVersion..." -ForegroundColor Cyan $url = "https://github.com/aquasecurity/tfsec/releases/download/v$TFSecVersion/tfsec-windows-amd64.exe" Invoke-WebRequest $url -OutFile 'C:\tools\tfsec\tfsec.exe' # Install Checkov pip install checkov==$CheckovVersion --quiet # Install terraform-docs choco install terraform-docs -y --no-progress ¦ Out-Null # Validate all tools Write-Host "`nValidating installed tools..." -ForegroundColor Green @('az --version','terraform --version','tflint --version','tfsec --version', 'checkov --version','helm version','kubectl version --client','terraform-docs --version') ¦ ForEach-Object { try { Invoke-Expression $_ ¦ Select-Object -First 1 ¦ Write-Host -ForegroundColor Gray } catch { Write-Warning "FAILED: $_" } } Write-Host "Bootstrap complete." -ForegroundColor Green

| PHASE 1 | Discover & Assess Azure Migrate, dependency mapping, inventory automation, wave prioritisation |
| --- | --- |

2.1  Sprint Tasks & Ownership

| Task ID | Activity | Duration | Owner | Tool |
| --- | --- | --- | --- | --- |
| P1-T01 | Deploy Azure Migrate appliance (VMware/Hyper-V OVA) | 3 days | Mig. Eng. | Azure Portal / PowerShell |
| P1-T02 | Configure discovery scope and credentials | 1 day | Mig. Eng. | PowerShell Az module |
| P1-T03 | Enable dependency analysis (agentless + agent-based) | 2 days | Mig. Eng. | Azure Migrate / MMA agent |
| P1-T04 | Run 30-day observation window — monitor discovery | 30 days | Mig. Eng. | Azure Migrate Hub |
| P1-T05 | Export discovered inventory via REST API | 1 day | Mig. Eng. | Python / PowerShell |
| P1-T06 | Validate inventory against CMDB | 2 days | Mig. Eng. + Client | Excel / Power BI |
| P1-T07 | Execute readiness assessments (VM, SQL, AKS, AppSvc) | 3 days | Mig. Eng. | Azure Migrate Assessments |
| P1-T08 | Automate wave prioritisation scoring | 2 days | Mig. Eng. | Python script |
| P1-T09 | Produce dependency maps per application group | 2 days | Mig. Eng. | Azure Migrate export / Visio |
| P1-T10 | Author migration wave plan document | 2 days | Cloud Architect | Word / Confluence |

2.2  Discovery Automation Scripts

Deploy Azure Migrate Appliance & Configure Discovery

PowerShell — P1-01-deploy-migrate-appliance.ps1

param( [Parameter(Mandatory)] [string]$ResourceGroupName, [Parameter(Mandatory)] [string]$ProjectName, [Parameter(Mandatory)] [string]$Location, [Parameter(Mandatory)] [string]$SubscriptionId ) # Authenticate and set context Connect-AzAccount -TenantId $env:ARM_TENANT_ID Set-AzContext -SubscriptionId $SubscriptionId # Create Resource Group if not exists Write-Host "Ensuring resource group: $ResourceGroupName" -ForegroundColor Cyan New-AzResourceGroup -Name $ResourceGroupName -Location $Location -Force ¦ Out-Null # Create Azure Migrate project $migrateProject = @{ ResourceGroupName = $ResourceGroupName Name = $ProjectName Location = $Location Sku = @{ Name = 'Standard' } Properties = @{} } $apiVersion = "2023-06-06" $resourceId = "/subscriptions/$SubscriptionId/resourceGroups/$ResourceGroupName/providers/Microsoft.Migrate/MigrateProjects/$ProjectName" Write-Host "Creating Azure Migrate project: $ProjectName" -ForegroundColor Cyan New-AzResource -ResourceId $resourceId -ApiVersion $apiVersion ` -Properties @{} -Location $Location -Force # Register required resource providers $providers = @( 'Microsoft.Migrate', 'Microsoft.OffAzure', 'Microsoft.DataMigration', 'Microsoft.HybridCompute' ) $providers ¦ ForEach-Object { Write-Host "Registering provider: $_" -ForegroundColor Gray Register-AzResourceProvider -ProviderNamespace $_ ¦ Out-Null } # Output appliance registration key for OVA deployment $keyUri = "$resourceId/solutions/Servers-Assessment-ServerAssessment/getConfig?api-version=$apiVersion" $config = Invoke-AzRestMethod -Path $keyUri -Method POST Write-Host "Appliance Key URI ready. Deploy OVA and register with key from Azure Migrate portal." -ForegroundColor Green Write-Host "Project Resource ID: $resourceId" -ForegroundColor Yellow

Export Discovered Inventory via REST API

Python — P1-02-export-inventory.py

#!/usr/bin/env python3 """Export Azure Migrate discovered servers to CSV for wave analysis.""" import os, json, csv, requests from azure.identity import DefaultAzureCredential from azure.mgmt.migrate import AzureMigrateV2 SUBSCRIPTION_ID = os.environ['AZURE_SUBSCRIPTION_ID'] RESOURCE_GROUP = os.environ['MIGRATE_RG'] PROJECT_NAME = os.environ['MIGRATE_PROJECT'] credential = DefaultAzureCredential() client = AzureMigrateV2(credential, SUBSCRIPTION_ID) def get_token(): token = credential.get_token('https://management.azure.com/.default') return token.token def export_servers(): headers = {'Authorization': f'Bearer {get_token()}', 'Content-Type': 'application/json'} base = 'https://management.azure.com' path = (f'/subscriptions/{SUBSCRIPTION_ID}/resourceGroups/{RESOURCE_GROUP}' f'/providers/Microsoft.Migrate/MigrateProjects/{PROJECT_NAME}' f'/solutions/Servers-Discovery-ServerDiscovery/databases' f'?api-version=2023-06-06') resp = requests.get(base + path, headers=headers) resp.raise_for_status() return resp.json().get('value', []) def score_workload(server: dict) -> dict: props = server.get('properties', {}) cores = props.get('numberOfProcessorCore', 0) mem = props.get('allocatedMemoryInMB', 0) / 1024 disks = len(props.get('disks', {})) # Complexity score: higher = migrate later score = (cores * 2) + (mem * 0.5) + (disks * 3) tier = 'T1-Critical' if score > 40 else ('T2-Standard' if score > 20 else 'T3-Simple') return { 'ServerName': props.get('displayName', 'Unknown'), 'OS': props.get('guestOSName', 'Unknown'), 'Cores': cores, 'MemoryGB': round(mem, 1), 'DiskCount': disks, 'ComplexityScore': round(score, 1), 'SuggestedTier': tier, 'PowerState': props.get('powerStatus', 'Unknown'), } servers = export_servers() print(f'Discovered {len(servers)} servers') scored = sorted([score_workload(s) for s in servers], key=lambda x: x['ComplexityScore']) with open('migration_inventory.csv', 'w', newline='') as f: writer = csv.DictWriter(f, fieldnames=scored[0].keys()) writer.writeheader() writer.writerows(scored) print('Exported: migration_inventory.csv') # Wave assignment: bottom 40% = Wave 1, middle 40% = Wave 2, top 20% = Wave 3 total = len(scored) for i, s in enumerate(scored): s['Wave'] = 'Wave-1' if i < total*0.4 else ('Wave-2' if i < total*0.8 else 'Wave-3') print(f" {s['ServerName']:30} Score:{s['ComplexityScore']:6.1f} -> {s['Wave']}")

Dependency Mapping — Enable MMA Agent at Scale

PowerShell — P1-03-enable-dependency-agents.ps1

param( [string]$WorkspaceResourceId, # Log Analytics workspace resource ID [string]$ResourceGroupFilter, # Filter VMs by resource group name pattern [string]$SubscriptionId ) Set-AzContext -SubscriptionId $SubscriptionId $vms = Get-AzVM ¦ Where-Object { $_.ResourceGroupName -like "*$ResourceGroupFilter*" } Write-Host "Found $($vms.Count) VMs matching filter: $ResourceGroupFilter" -ForegroundColor Cyan $results = @() foreach ($vm in $vms) { Write-Host " Processing: $($vm.Name)" -ForegroundColor Gray try { # Install MMA extension $mmaExt = @{ VMName = $vm.Name ResourceGroupName = $vm.ResourceGroupName Location = $vm.Location Name = 'MicrosoftMonitoringAgent' Publisher = 'Microsoft.EnterpriseCloud.Monitoring' ExtensionType = 'MicrosoftMonitoringAgent' TypeHandlerVersion= '1.0' Settings = @{ workspaceId = (Get-AzOperationalInsightsWorkspace ¦ Where-Object ResourceId -eq $WorkspaceResourceId).CustomerId } ProtectedSettings = @{ workspaceKey = (Get-AzOperationalInsightsWorkspaceSharedKey -ResourceGroupName ($WorkspaceResourceId -split '/')[4] -Name ($WorkspaceResourceId -split '/')[-1]).PrimarySharedKey } } Set-AzVMExtension @mmaExt -Force ¦ Out-Null # Install Dependency agent $depExt = @{ VMName = $vm.Name ResourceGroupName = $vm.ResourceGroupName Location = $vm.Location Name = 'DependencyAgentWindows' Publisher = 'Microsoft.Azure.Monitoring.DependencyAgent' ExtensionType = 'DependencyAgentWindows' TypeHandlerVersion= '9.10' } Set-AzVMExtension @depExt -Force ¦ Out-Null $ $results += [PSCustomObject]@{ VM=$vm.Name; Status="Success" } } catch { $ $results += [PSCustomObject]@{ VM=$vm.Name; Status="Failed: $_" } } } $results ¦ Export-Csv "dependency-agent-status.csv" -NoTypeInformation Write-Host "Done. Results: dependency-agent-status.csv" -ForegroundColor Green

2.3  Phase 1 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| Azure Migrate project deployed | P1-01-deploy-migrate-appliance.ps1 | Mig. Eng. | S1 |
| Discovery inventory CSV (scored & waved) | P1-02-export-inventory.py | Mig. Eng. | S1 |
| Dependency agents deployed at scale | P1-03-enable-dependency-agents.ps1 | Mig. Eng. | S1 |
| Readiness assessment report | Azure Migrate portal export | Mig. Eng. | S2 |
| Wave prioritisation matrix (Excel) | P1-02 output + manual review | Cloud Arch. | S2 |
| Migration wave plan document | Word template + ARB sign-off | Cloud Arch. | S2 |

| PHASE 2 | Design & Landing Zone Terraform module library, hub-spoke networking, identity, governance baseline |
| --- | --- |

3.1  Repository & Module Library Structure

All Terraform code lives in Azure Repos. The module library is a dedicated repository (infra-migration-patterns) with semantic versioning. Landing Zone infrastructure is a separate repository (infra-landing-zone) that consumes modules from the library.

Bash — P2-00-repo-init.sh

#!/usr/bin/env bash # Initialise Azure DevOps project, repositories and branch policies set -euo pipefail ORG='https://dev.azure.com/YOUR-ORG' PROJECT='azure-migration' az devops configure --defaults organization=$ORG project=$PROJECT # Create repositories for REPO in infra-landing-zone infra-migration-patterns pipelines-templates migration-governance migration-automation; do echo "Creating repo: $REPO" az repos create --name $REPO --project $PROJECT 2>/dev/null ¦¦ echo " Already exists: $REPO" done # Apply branch policies to main branches (require PR + min 1 reviewer) for REPO in infra-landing-zone infra-migration-patterns migration-governance; do REPO_ID=$(az repos show --repository $REPO --query id -o tsv) az repos policy approver-count create \ --repository-id $REPO_ID --branch main \ --minimum-approver-count 1 --creator-vote-counts false \ --allow-downvotes false --reset-on-source-push true \ --blocking true echo "Branch policy applied: $REPO/main" done echo 'Repositories and branch policies configured.'

3.2  Landing Zone — Terraform Module Library

Module: Hub-Spoke Networking

The networking module deploys the full hub VNet with Azure Firewall, ExpressRoute/VPN Gateway, Bastion, Private DNS Resolver, and spoke VNet peering. Parameterised for all environments.

HCL — modules/networking/hub-spoke/main.tf

terraform { required_providers { azurerm = { source = "hashicorp/azurerm", version = "~> 3.100" } } } # ── Hub Virtual Network ─────────────────────────────────────────────── resource "azurerm_virtual_network" "hub" { name = "vnet-hub-${var.environment}-${var.location_short}" resource_group_name = var.hub_resource_group_name location = var.location address_space = [var.hub_address_space] dns_servers = var.custom_dns_servers tags = local.common_tags } resource "azurerm_subnet" "azure_firewall" { name = "AzureFirewallSubnet" resource_group_name = var.hub_resource_group_name virtual_network_name = azurerm_virtual_network.hub.name address_prefixes = [var.firewall_subnet_prefix] } resource "azurerm_subnet" "gateway" { name = "GatewaySubnet" resource_group_name = var.hub_resource_group_name virtual_network_name = azurerm_virtual_network.hub.name address_prefixes = [var.gateway_subnet_prefix] } resource "azurerm_subnet" "bastion" { name = "AzureBastionSubnet" resource_group_name = var.hub_resource_group_name virtual_network_name = azurerm_virtual_network.hub.name address_prefixes = [var.bastion_subnet_prefix] } # ── Azure Firewall Premium ──────────────────────────────────────────── resource "azurerm_public_ip" "firewall" { name = "pip-fw-${var.environment}-${var.location_short}" resource_group_name = var.hub_resource_group_name location = var.location allocation_method = "Static" sku = "Standard" tags = local.common_tags } resource "azurerm_firewall" "hub" { name = "fw-hub-${var.environment}-${var.location_short}" resource_group_name = var.hub_resource_group_name location = var.location sku_name = "AZFW_VNet" sku_tier = "Premium" firewall_policy_id = azurerm_firewall_policy.hub.id ip_configuration { name = "ipconfig" subnet_id = azurerm_subnet.azure_firewall.id public_ip_address_id = azurerm_public_ip.firewall.id } tags = local.common_tags } resource "azurerm_firewall_policy" "hub" { name = "fwpol-hub-${var.environment}" resource_group_name = var.hub_resource_group_name location = var.location sku = "Premium" threat_intelligence_mode = "Alert" intrusion_detection { mode = "Alert" } tags = local.common_tags } # ── Spoke VNet & Peering ────────────────────────────────────────────── resource "azurerm_virtual_network" "spoke" { for_each = var.spokes name = "vnet-${each.key}-${var.environment}-${var.location_short}" resource_group_name = each.value.resource_group_name location = var.location address_space = [each.value.address_space] dns_servers = var.custom_dns_servers tags = merge(local.common_tags, each.value.tags) } resource "azurerm_virtual_network_peering" "hub_to_spoke" { for_each = var.spokes name = "peer-hub-to-${each.key}" resource_group_name = var.hub_resource_group_name virtual_network_name = azurerm_virtual_network.hub.name remote_virtual_network_id = azurerm_virtual_network.spoke[each.key].id allow_forwarded_traffic = true allow_gateway_transit = true } resource "azurerm_virtual_network_peering" "spoke_to_hub" { for_each = var.spokes name = "peer-${each.key}-to-hub" resource_group_name = each.value.resource_group_name virtual_network_name = azurerm_virtual_network.spoke[each.key].name remote_virtual_network_id = azurerm_virtual_network.hub.id use_remote_gateways = true } locals { common_tags = { Environment = var.environment ManagedBy = "Terraform" Programme = "AzureMigration" CostCentre = var.cost_centre Owner = var.owner } }

Module: Identity & RBAC Baseline

HCL — modules/identity/rbac-baseline/main.tf

# RBAC Baseline — creates AAD groups, role assignments, managed identities # and enforces PIM-eligible assignments for privileged roles resource "azuread_group" "groups" { for_each = var.aad_groups display_name = each.value.display_name security_enabled = true description = each.value.description } # Assign roles to groups at subscription or resource group scope resource "azurerm_role_assignment" "group_assignments" { for_each = var.role_assignments scope = each.value.scope role_definition_name = each.value.role principal_id = azuread_group.groups[each.value.group_key].object_id } # Workload managed identity — no SP credentials, RBAC-scoped resource "azurerm_user_assigned_identity" "workload" { for_each = var.workload_identities name = "id-${each.key}-${var.environment}" resource_group_name = each.value.resource_group_name location = var.location tags = local.common_tags } resource "azurerm_role_assignment" "workload_identity" { for_each = var.workload_identity_roles scope = each.value.scope role_definition_name = each.value.role principal_id = azurerm_user_assigned_identity.workload[each.value.identity_key].principal_id } # Pipeline service principal — Reader on subscription, Contributor on target RG only resource "azurerm_role_assignment" "pipeline_sp" { scope = var.pipeline_target_rg_id role_definition_name = "Contributor" principal_id = var.pipeline_sp_object_id }

Module: Management Group Hierarchy & Subscription Placement

HCL — modules/governance/management-groups/main.tf

# CAF-aligned Management Group hierarchy # Root > Platform > (Identity, Management, Connectivity) # > LandingZones > (Corp, Online) # > Sandboxes resource "azurerm_management_group" "platform" { name = "${var.prefix}-Platform" display_name = "Platform" parent_management_group_id = data.azurerm_management_group.root.id } resource "azurerm_management_group" "landing_zones" { name = "${var.prefix}-LandingZones" display_name = "Landing Zones" parent_management_group_id = data.azurerm_management_group.root.id } resource "azurerm_management_group" "corp" { name = "${var.prefix}-Corp" display_name = "Corp" parent_management_group_id = azurerm_management_group.landing_zones.id } resource "azurerm_management_group" "sandboxes" { name = "${var.prefix}-Sandboxes" display_name = "Sandboxes" parent_management_group_id = data.azurerm_management_group.root.id } # Associate subscriptions resource "azurerm_management_group_subscription_association" "corp" { for_each = toset(var.corp_subscription_ids) management_group_id = azurerm_management_group.corp.id subscription_id = each.value } data "azurerm_management_group" "root" { name = var.root_management_group_name }

3.3  Terraform Remote State & Backend Setup

PowerShell — P2-01-setup-tf-backend.ps1

param( [string]$ResourceGroupName = 'rg-tfstate-prod', [string]$Location = 'uksouth', [string]$StorageAccountName, # globally unique [string]$ContainerName = 'tfstate', [string]$SubscriptionId ) Set-AzContext -SubscriptionId $SubscriptionId # Create resource group for Terraform state New-AzResourceGroup -Name $ResourceGroupName -Location $Location -Force # Create storage account with soft-delete, versioning, private access only $sa = New-AzStorageAccount -ResourceGroupName $ResourceGroupName ` -Name $StorageAccountName -Location $Location ` -SkuName 'Standard_GRS' -Kind 'StorageV2' ` -AllowBlobPublicAccess $false ` -MinimumTlsVersion 'TLS1_2' ` -EnableHttpsTrafficOnly $true # Enable versioning and soft-delete Enable-AzStorageBlobDeleteRetentionPolicy -ResourceGroupName $ResourceGroupName ` -StorageAccountName $StorageAccountName -RetentionDays 30 $ctx = $sa.Context Enable-AzStorageBlobRestorePolicy -ResourceGroupName $ResourceGroupName ` -StorageAccountName $StorageAccountName -RestoreDays 29 # Create state container New-AzStorageContainer -Name $ContainerName -Context $ctx -Permission Off # Lock resource group against accidental deletion New-AzResourceLock -LockName 'tfstate-lock' -LockLevel CanNotDelete ` -ResourceGroupName $ResourceGroupName -Force Write-Host @" Terraform backend ready. Add to your backend.tf: terraform { backend "azurerm" { resource_group_name = "$ResourceGroupName" storage_account_name = "$StorageAccountName" container_name = "$ContainerName" key = "<workload>.tfstate" } } "@

3.4  Phase 2 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| Azure Repos + branch policies configured | P2-00-repo-init.sh | Mig. Eng. | S3 |
| Terraform remote state backend | P2-01-setup-tf-backend.ps1 | Mig. Eng. | S3 |
| Hub-Spoke networking module (v1.0.0) | modules/networking/hub-spoke/ | Mig. Eng. | S3 |
| Identity & RBAC baseline module (v1.0.0) | modules/identity/rbac-baseline/ | Mig. Eng. | S4 |
| Management Group hierarchy module (v1.0.0) | modules/governance/management-groups/ | Mig. Eng. | S4 |
| Landing Zone deployed to DEV | infra-landing-zone/envs/dev/ | Mig. Eng. | S5 |
| Landing Zone deployed to PROD | infra-landing-zone/envs/prod/ | Cloud Arch. | S5 |

| PHASE 3 | Build & Automate Azure DevOps pipeline templates, policy automation, module CI/CD, testing gates |
| --- | --- |

4.1  Standard Terraform CI/CD Pipeline

Every repository that contains Terraform code consumes the reusable pipeline template below. The template enforces all quality gates and is stored in pipelines-templates/terraform-cicd.yml. Individual repos reference it with a single resource block.

YAML — pipelines-templates/terraform-cicd.yml

# Reusable Terraform CI/CD pipeline template # Consumed by all infra repos via: template: terraform-cicd.yml@pipelines-templates parameters: - name: environment type: string values: [dev, qa, prod] - name: workingDirectory type: string default: '.' - name: backendKey type: string - name: destroyApprovalRequired type: boolean default: true stages: # ── Stage 1: Static Analysis ──────────────────────────────────────── - stage: Lint_and_Security displayName: '1 — Lint & Security Scan' jobs: - job: static_analysis pool: { vmImage: ubuntu-latest } steps: - checkout: self - script: ¦ terraform fmt -check -recursive ${{ parameters.workingDirectory }} displayName: 'terraform fmt --check' failOnStderr: false - script: ¦ terraform init -backend=false ${{ parameters.workingDirectory }} terraform validate ${{ parameters.workingDirectory }} displayName: 'terraform validate' - script: ¦ tflint --init tflint --chdir=${{ parameters.workingDirectory }} --format=compact displayName: 'tflint' env: TFLINT_LOG: warn - script: ¦ tfsec ${{ parameters.workingDirectory }} \ --severity HIGH \ --format lovely \ --no-colour \ --exit-code 1 displayName: 'tfsec (HIGH/CRITICAL gate)' - script: ¦ checkov -d ${{ parameters.workingDirectory }} \ --framework terraform \ --compact --output cli \ --soft-fail-on MEDIUM \ --hard-fail-on HIGH,CRITICAL displayName: 'Checkov CIS benchmark' # ── Stage 2: Terraform Plan ────────────────────────────────────────── - stage: Plan displayName: '2 — Terraform Plan' dependsOn: Lint_and_Security jobs: - job: terraform_plan pool: { vmImage: ubuntu-latest } steps: - checkout: self - task: AzureCLI@2 displayName: 'terraform init' inputs: azureSubscription: $(SERVICE_CONNECTION) scriptType: bash scriptLocation: inlineScript inlineScript: ¦ terraform init \ -backend-config="resource_group_name=$(TF_BACKEND_RG)" \ -backend-config="storage_account_name=$(TF_BACKEND_SA)" \ -backend-config="container_name=tfstate" \ -backend-config="key=${{ parameters.backendKey }}" \ ${{ parameters.workingDirectory }} env: ARM_CLIENT_ID: $(ARM_CLIENT_ID) ARM_CLIENT_SECRET: $(ARM_CLIENT_SECRET) ARM_TENANT_ID: $(ARM_TENANT_ID) ARM_SUBSCRIPTION_ID: $(ARM_SUBSCRIPTION_ID) - task: AzureCLI@2 displayName: 'terraform plan' inputs: azureSubscription: $(SERVICE_CONNECTION) scriptType: bash scriptLocation: inlineScript inlineScript: ¦ terraform plan \ -var-file=envs/${{ parameters.environment }}/terraform.tfvars \ -out=tfplan \ -input=false \ ${{ parameters.workingDirectory }} terraform show -json tfplan > tfplan.json env: ARM_CLIENT_ID: $(ARM_CLIENT_ID) ARM_CLIENT_SECRET: $(ARM_CLIENT_SECRET) ARM_TENANT_ID: $(ARM_TENANT_ID) ARM_SUBSCRIPTION_ID: $(ARM_SUBSCRIPTION_ID) - task: PublishPipelineArtifact@1 inputs: targetPath: tfplan artifact: tfplan-${{ parameters.environment }} # ── Stage 3: Approval Gate ─────────────────────────────────────────── - stage: Approval displayName: '3 — Plan Review & Approval' dependsOn: Plan jobs: - job: await_approval pool: server timeoutInMinutes: 4320 # 3-day approval window steps: - task: ManualValidation@0 inputs: notifyUsers: ¦ $(APPROVER_EMAIL_1) $(APPROVER_EMAIL_2) instructions: ¦ Review the Terraform plan artifact (tfplan-${{ parameters.environment }}). Approve only if: no unexpected destroys, diff matches sprint scope. onTimeout: reject # ── Stage 4: Terraform Apply ───────────────────────────────────────── - stage: Apply displayName: '4 — Terraform Apply' dependsOn: Approval jobs: - deployment: terraform_apply environment: ${{ parameters.environment }} pool: { vmImage: ubuntu-latest } strategy: runOnce: deploy: steps: - task: AzureCLI@2 displayName: 'terraform apply' inputs: azureSubscription: $(SERVICE_CONNECTION) scriptType: bash scriptLocation: inlineScript inlineScript: ¦ terraform apply -input=false -auto-approve \ $(Pipeline.Workspace)/tfplan-${{ parameters.environment }}/tfplan env: ARM_CLIENT_ID: $(ARM_CLIENT_ID) ARM_CLIENT_SECRET: $(ARM_CLIENT_SECRET) ARM_TENANT_ID: $(ARM_TENANT_ID) ARM_SUBSCRIPTION_ID: $(ARM_SUBSCRIPTION_ID) # ── Stage 5: Post-Apply Tests ───────────────────────────────────────── - stage: PostApply_Tests displayName: '5 — Post-Apply Validation' dependsOn: Apply jobs: - job: validate pool: { vmImage: ubuntu-latest } steps: - task: AzureCLI@2 displayName: 'Run post-apply validation script' inputs: azureSubscription: $(SERVICE_CONNECTION) scriptType: bash scriptLocation: inlineScript inlineScript: ¦ python migration-automation/tests/post_apply_validate.py \ --env ${{ parameters.environment }} \ --subscription $(ARM_SUBSCRIPTION_ID) # ── Stage 6: Compliance Check ───────────────────────────────────────── - stage: Compliance displayName: '6 — Azure Policy Compliance' dependsOn: PostApply_Tests jobs: - job: policy_check pool: { vmImage: ubuntu-latest } steps: - task: AzureCLI@2 displayName: 'Check Azure Policy compliance' inputs: azureSubscription: $(SERVICE_CONNECTION) scriptType: bash scriptLocation: inlineScript inlineScript: ¦ python migration-automation/tests/policy_compliance_check.py \ --subscription $(ARM_SUBSCRIPTION_ID) \ --fail-on-noncompliant

4.2  Azure Policy Initiative — Governance Automation

Deploy Policy Initiative via Terraform

HCL — modules/governance/policy-initiative/main.tf

# Deploys the mandatory migration governance policy initiative # covering: location restrictions, tagging, diagnostics, security resource "azurerm_policy_set_definition" "migration_governance" { name = "migration-governance-initiative" policy_type = "Custom" display_name = "Azure Migration Governance Initiative" description = "Mandatory guardrails for all migration wave subscriptions" management_group_id = var.management_group_id metadata = jsonencode({ category = "Migration Governance" }) parameters = jsonencode({ allowedLocations = { type = "Array" } logAnalyticsWorkspaceId = { type = "String" } requiredTagNames = { type = "Array" } }) # 1. Allowed locations policy_definition_reference { policy_definition_id = "/providers/Microsoft.Authorization/policyDefinitions/e56962a6-4747-49cd-b67b-bf8b01975c4f" parameter_values = jsonencode({ listOfAllowedLocations = { value = "[parameters('allowedLocations')]" } }) } # 2. Diagnostic settings — deploy if not exists policy_definition_reference { policy_definition_id = azurerm_policy_definition.diag_settings.id parameter_values = jsonencode({ workspaceId = { value = "[parameters('logAnalyticsWorkspaceId')]" } }) } # 3. Require mandatory tags policy_definition_reference { policy_definition_id = azurerm_policy_definition.require_tags.id parameter_values = jsonencode({ tagNames = { value = "[parameters('requiredTagNames')]" } }) } # 4. No public IP on VMs policy_definition_reference { policy_definition_id = "/providers/Microsoft.Authorization/policyDefinitions/9dcbebd3-7b89-4b80-bfdf-6b3cfbe5b5ea" } # 5. Require HTTPS on storage policy_definition_reference { policy_definition_id = "/providers/Microsoft.Authorization/policyDefinitions/404c3081-a854-4457-ae30-26a93ef643f9" } } resource "azurerm_management_group_policy_assignment" "migration_governance" { name = "migration-governance" management_group_id = var.management_group_id policy_definition_id = azurerm_policy_set_definition.migration_governance.id location = var.location identity { type = "SystemAssigned" } parameters = jsonencode({ allowedLocations = { value = var.allowed_locations } logAnalyticsWorkspaceId = { value = var.log_analytics_workspace_id } requiredTagNames = { value = ["Environment","WorkloadName","CostCentre","Owner","MigrationWave"] } }) } # Custom policy: require diagnostic settings on all compute resource "azurerm_policy_definition" "diag_settings" { name = "require-diagnostic-settings" policy_type = "Custom" mode = "All" display_name = "Deploy diagnostic settings to Log Analytics" management_group_id = var.management_group_id policy_rule = file("${path.module}/policies/diag-settings-rule.json") parameters = file("${path.module}/policies/diag-settings-params.json") }

4.3  Post-Apply Validation Script

Python — migration-automation/tests/post_apply_validate.py

#!/usr/bin/env python3 """Post-apply infrastructure validation — runs after every terraform apply.""" import argparse, sys, json from azure.identity import DefaultAzureCredential from azure.mgmt.network import NetworkManagementClient from azure.mgmt.resource import ResourceManagementClient from azure.mgmt.monitor import MonitorManagementClient parser = argparse.ArgumentParser() parser.add_argument('--subscription', required=True) parser.add_argument('--env', required=True) args = parser.parse_args() cred = DefaultAzureCredential() net_cl = NetworkManagementClient(cred, args.subscription) res_cl = ResourceManagementClient(cred, args.subscription) mon_cl = MonitorManagementClient(cred, args.subscription) PASS, FAIL = ' PASS', ' FAIL' results = [] def check(name, fn): try: ok, detail = fn() results.append((name, ok, detail)) print(f"{PASS if ok else FAIL} {name}: {detail}") except Exception as e: results.append((name, False, str(e))) print(f"{FAIL} {name}: EXCEPTION — {e}") # ── Checks ──────────────────────────────────────────────────────────── def check_hub_vnet(): vnets = list(net_cl.virtual_networks.list_all()) hub = next((v for v in vnets if 'hub' in v.name.lower()), None) return (hub is not None, hub.name if hub else 'Hub VNet not found') def check_firewall(): fws = list(net_cl.azure_firewalls.list_all()) fw = next((f for f in fws if f.provisioning_state == 'Succeeded'), None) return (fw is not None, fw.name if fw else 'No provisioned firewall') def check_no_public_ips_on_vms(): nics = list(net_cl.network_interfaces.list_all()) violations = [] for nic in nics: if nic.virtual_machine: for ipc in (nic.ip_configurations or []): if ipc.public_ip_address: violations.append(nic.name) return (len(violations)==0, 'All VMs private' if not violations else f'Public IPs on: {violations}') def check_peerings_connected(): vnets = list(net_cl.virtual_networks.list_all()) broken = [] for vn in vnets: for peer in net_cl.virtual_network_peerings.list(vn.id.split('/')[4], vn.name): if peer.peering_state != 'Connected': broken.append(f'{vn.name}/{peer.name}') return (len(broken)==0, 'All peerings connected' if not broken else f'Broken: {broken}') # Run all checks check('Hub VNet exists', check_hub_vnet) check('Azure Firewall provisioned', check_firewall) check('No public IPs on VMs', check_no_public_ips_on_vms) check('All VNet peerings connected', check_peerings_connected) # ── Summary ──────────────────────────────────────────────────────────── failed = [r for r in results if not r[1]] print(f'\n{len(results)-len(failed)}/{len(results)} checks passed.') if failed: print(f'FAILED checks: {[r[0] for r in failed]}') sys.exit(1) print('All post-apply validations passed.')

4.4  Phase 3 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| Reusable CI/CD pipeline template published | pipelines-templates/terraform-cicd.yml | Mig. Eng. | S6 |
| Policy initiative Terraform module (v1.0.0) | modules/governance/policy-initiative/ | Mig. Eng. | S6 |
| Diagnostic settings custom policy JSON | policies/diag-settings-rule.json | Mig. Eng. | S6 |
| Post-apply validation test suite | migration-automation/tests/post_apply_validate.py | Mig. Eng. | S7 |
| Policy compliance check script | migration-automation/tests/policy_compliance_check.py | Mig. Eng. | S7 |
| tflint + tfsec config files (.tflint.hcl, .tfsec/) | repo root configs | Mig. Eng. | S7 |
| Module README automation (terraform-docs CI step) | pipelines-templates/terraform-cicd.yml | Mig. Eng. | S8 |
| All module READMEs auto-generated and committed | infra-migration-patterns/ | Mig. Eng. | S8 |

| PHASE 4 | Migrate & Execute ASR replication, wave orchestration, cutover scripts, smoke tests, rollback |
| --- | --- |

5.1  ASR Replication Setup — Terraform

HCL — modules/migration/asr-replication/main.tf

# Azure Site Recovery — Replication for Rehost (Lift & Shift) pattern resource "azurerm_recovery_services_vault" "migration" { name = "rsv-migration-${var.environment}-${var.location_short}" resource_group_name = var.resource_group_name location = var.location sku = "Standard" soft_delete_enabled = true tags = var.common_tags } resource "azurerm_site_recovery_fabric" "primary" { name = "fabric-primary-${var.source_location_short}" resource_group_name = var.resource_group_name recovery_vault_name = azurerm_recovery_services_vault.migration.name location = var.source_location } resource "azurerm_site_recovery_fabric" "target" { name = "fabric-target-${var.location_short}" resource_group_name = var.resource_group_name recovery_vault_name = azurerm_recovery_services_vault.migration.name location = var.location } resource "azurerm_site_recovery_protection_container" "primary" { name = "pc-primary" resource_group_name = var.resource_group_name recovery_vault_name = azurerm_recovery_services_vault.migration.name recovery_fabric_name = azurerm_site_recovery_fabric.primary.name } resource "azurerm_site_recovery_protection_container" "target" { name = "pc-target" resource_group_name = var.resource_group_name recovery_vault_name = azurerm_recovery_services_vault.migration.name recovery_fabric_name = azurerm_site_recovery_fabric.target.name } resource "azurerm_site_recovery_replication_policy" "vmware" { name = "pol-vmware-24h" resource_group_name = var.resource_group_name recovery_vault_name = azurerm_recovery_services_vault.migration.name recovery_point_retention_in_minutes = 1440 # 24 hours application_consistent_snapshot_frequency_in_minutes = 60 }

Cutover Orchestration Script

PowerShell — P4-01-wave-cutover.ps1

#Requires -Modules Az.RecoveryServices, Az.Network, Az.Compute param( [Parameter(Mandatory)] [string]$VaultName, [Parameter(Mandatory)] [string]$VaultResourceGroup, [Parameter(Mandatory)] [string[]]$VMNames, # Array of VM names to cut over [Parameter(Mandatory)] [string]$TargetResourceGroup, [Parameter(Mandatory)] [string]$DnsZoneName, # Private DNS zone [Parameter(Mandatory)] [string]$DnsResourceGroup, [switch]$WhatIf ) Set-StrictMode -Version Latest; $ErrorActionPreference = "Stop" $vault = Get-AzRecoveryServicesVault -Name $VaultName -ResourceGroupName $VaultResourceGroup Set-AzRecoveryServicesVaultContext -Vault $vault function Invoke-CutoverStep([string]$Description, [scriptblock]$Action) { Write-Host "[$([datetime]::Now.ToString("HH:mm:ss"))] $Description" -ForegroundColor Cyan if (-not $WhatIf) { & $Action } else { Write-Host " [WhatIf] Skipped." -ForegroundColor Yellow } } # ── Pre-cutover validations ──────────────────────────────────────────── Write-Host "=== PRE-CUTOVER VALIDATION ===" -ForegroundColor Yellow foreach ($vmName in $VMNames) { $ $item = Get-AzRecoveryServicesAsrReplicationProtectedItem ¦ Where-Object { $_.FriendlyName -eq $vmName } if (-not $item) { throw "VM $vmName not found in ASR protected items" } if ($item.ReplicationHealth -ne "Normal") { throw "$vmName replication health: $($item.ReplicationHealth)" } $ $lag = $item.RecoveryPointObjective if ($lag -gt 300) { Write-Warning "$vmName replication lag ${lag}s exceeds 5min threshold" } Write-Host " PASS: $vmName — Health:$($item.ReplicationHealth) Lag:${lag}s" -ForegroundColor Green } # ── Quiesce source workloads ────────────────────────────────────────── Invoke-CutoverStep 'Quiesce source application (stop services)' { # Customise per workload — example: stop IIS # Invoke-AzVMRunCommand -VMName $srcVM -CommandId 'RunPowerShellScript' # -ScriptString 'Stop-Service -Name W3SVC' Write-Host ' Application services quiesced.' -ForegroundColor Gray } # ── Trigger planned failover for each VM ────────────────────────────── foreach ($vmName in $VMNames) { Invoke-CutoverStep "Initiating planned failover: $vmName" { $ $item = Get-AzRecoveryServicesAsrReplicationProtectedItem ¦ Where-Object { $_.FriendlyName -eq $vmName } Start-AzRecoveryServicesAsrPlannedFailoverJob -ReplicationProtectedItem $item ` -Direction PrimaryToRecovery ¦ Out-Null } } # ── Wait for failovers to complete ──────────────────────────────────── Invoke-CutoverStep 'Waiting for failover jobs to complete (max 60 min)' { $timeout = (Get-Date).AddMinutes(60) do { Start-Sleep -Seconds 30 $ $pending = Get-AzRecoveryServicesAsrJob ¦ Where-Object { $_.State -eq "InProgress" } Write-Host " Pending jobs: $($pending.Count)" -ForegroundColor Gray } while ($pending.Count -gt 0 -and (Get-Date) -lt $timeout) if ((Get-Date) -ge $timeout) { throw "Failover timeout exceeded" } } # ── DNS cutover ─────────────────────────────────────────────────────── foreach ($vmName in $VMNames) { Invoke-CutoverStep "DNS cutover: $vmName" { $ $vm = Get-AzVM -ResourceGroupName $TargetResourceGroup -Name $vmName $ $nic = Get-AzNetworkInterface -ResourceId $vm.NetworkProfile.NetworkInterfaces[0].Id $ $privateIp = $nic.IpConfigurations[0].PrivateIpAddress Remove-AzPrivateDnsRecordSet -ZoneName $DnsZoneName ` -ResourceGroupName $DnsResourceGroup -Name $vmName -RecordType A -ErrorAction SilentlyContinue New-AzPrivateDnsRecordSet -ZoneName $DnsZoneName ` -ResourceGroupName $DnsResourceGroup -Name $vmName -RecordType A -Ttl 300 ` -PrivateDnsRecords (New-AzPrivateDnsRecordConfig -IPv4Address $privateIp) Write-Host " DNS updated: $vmName -> $privateIp" -ForegroundColor Gray } } Write-Host "=== CUTOVER COMPLETE — INITIATING SMOKE TESTS ===" -ForegroundColor Green python smoke_tests/run_wave_smoke_tests.py --vms ($VMNames -join ',')

Smoke Test Suite

Python — smoke_tests/run_wave_smoke_tests.py

#!/usr/bin/env python3 """Post-cutover smoke test suite — validates each migrated VM.""" import argparse, sys, socket, subprocess, requests, time from azure.identity import DefaultAzureCredential from azure.mgmt.compute import ComputeManagementClient from azure.mgmt.network import NetworkManagementClient parser = argparse.ArgumentParser() parser.add_argument('--vms', required=True, help='Comma-separated VM names') parser.add_argument('--subscription', default=__import__('os').environ.get('AZURE_SUBSCRIPTION_ID')) parser.add_argument('--rg', required=False, default='') args = parser.parse_args() cred = DefaultAzureCredential() compute = ComputeManagementClient(cred, args.subscription) network = NetworkManagementClient(cred, args.subscription) vms = [v.strip() for v in args.vms.split(',')] results = [] def test(name, fn): try: ok, detail = fn() status = 'PASS' if ok else 'FAIL' print(f' [{status}] {name}: {detail}') results.append((name, ok)) except Exception as e: print(f' [FAIL] {name}: {e}') results.append((name, False)) for vm_name in vms: print(f'\n--- Smoke tests: {vm_name} ---') # 1. VM running state def vm_running(): vms_list = list(compute.virtual_machines.list_all()) vm = next((v for v in vms_list if v.name == vm_name), None) if not vm: return False, 'VM not found' iv = compute.virtual_machines.instance_view(vm.id.split('/')[4], vm_name) states = [s.code for s in iv.statuses] running = any('running' in s for s in states) return running, ' ¦ '.join(states) test('VM in running state', vm_running) # 2. DNS resolution def dns_resolves(): try: ip = socket.gethostbyname(vm_name) return True, f'Resolves to {ip}' except socket.gaierror as e: return False, str(e) test('DNS resolution', dns_resolves) # 3. SSH/RDP port reachable (port 22 for Linux, 3389 for Windows) def port_reachable(): for port in [22, 3389]: s = socket.socket() s.settimeout(5) if s.connect_ex((vm_name, port)) == 0: s.close() return True, f'Port {port} reachable' return False, 'Neither SSH(22) nor RDP(3389) reachable' test('Management port reachable', port_reachable) # 4. No public IP on NIC def no_public_ip(): nics = list(network.network_interfaces.list_all()) vm_nics = [n for n in nics if n.virtual_machine and vm_name in (n.virtual_machine.id or '')] for nic in vm_nics: for ipc in nic.ip_configurations: if ipc.public_ip_address: return False, f'Public IP found on NIC {nic.name}' return True, 'No public IPs' test('No public IP attached', no_public_ip) # Summary failed = [r[0] for r in results if not r[1]] total = len(results) passed = total - len(failed) print(f'\nSmoke tests: {passed}/{total} passed.') if failed: print(f'FAILURES: {failed}') sys.exit(1) print('All smoke tests passed. Cutover validated.')

Rollback Script

PowerShell — P4-02-rollback-failback.ps1

param( [Parameter(Mandatory)] [string]$VaultName, [Parameter(Mandatory)] [string]$VaultResourceGroup, [Parameter(Mandatory)] [string[]]$VMNames, [Parameter(Mandatory)] [string]$RollbackReason ) Write-Host "=== INITIATING ROLLBACK ===" -ForegroundColor Red Write-Host "Reason: $RollbackReason" -ForegroundColor Yellow Write-Host "$(Get-Date -Format "yyyy-MM-dd HH:mm:ss") — Rollback authorised" -ForegroundColor Gray $vault = Get-AzRecoveryServicesVault -Name $VaultName -ResourceGroupName $VaultResourceGroup Set-AzRecoveryServicesVaultContext -Vault $vault foreach ($vmName in $VMNames) { Write-Host "Re-protecting and failing back: $vmName" -ForegroundColor Cyan $ $item = Get-AzRecoveryServicesAsrReplicationProtectedItem ¦ Where-Object { $_.FriendlyName -eq $vmName } # Commit the failover first (required before re-protect) Start-AzRecoveryServicesAsrCommitFailoverJob -ReplicationProtectedItem $item ¦ Out-Null Start-Sleep -Seconds 60 # Re-protect to source Update-AzRecoveryServicesAsrProtectionDirection ` -ReplicationProtectedItem $item ` -Direction RecoveryToPrimary ¦ Out-Null Write-Host " $vmName: re-protection initiated." -ForegroundColor Gray } # Log rollback event to Log Analytics $body = @{ RollbackVMs=$VMNames; Reason=$RollbackReason; Timestamp=(Get-Date -Format "o") } ¦ ConvertTo-Json Invoke-RestMethod -Uri $env:LOG_ANALYTICS_WEBHOOK_URI -Method Post -Body $body -ContentType 'application/json' Write-Host "Rollback initiated. Monitor ASR for re-protection completion." -ForegroundColor Yellow

5.2  Phase 4 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| ASR vault + replication policy (Terraform) | modules/migration/asr-replication/ | Mig. Eng. | S9 |
| Wave cutover orchestration script | P4-01-wave-cutover.ps1 | Mig. Eng. | S9 |
| Post-cutover smoke test suite | smoke_tests/run_wave_smoke_tests.py | Mig. Eng. | S9 |
| Rollback / failback script | P4-02-rollback-failback.ps1 | Mig. Eng. | S9 |
| Wave 1 cutover complete + validated | Smoke tests green, ARB sign-off | Mig. Eng. | S10 |
| Wave 2 cutover complete + validated | Smoke tests green, ARB sign-off | Mig. Eng. | S11 |
| Wave 3 cutover complete + validated | Smoke tests green, ARB sign-off | Mig. Eng. | S12 |
| Decommission runbook (source VMs) | P4-03-decommission-source.ps1 | Mig. Eng. | S12 |

| PHASE 5 | Govern & Secure Defender for Cloud, FinOps, Key Vault, Sentinel, compliance reporting |
| --- | --- |

6.1  Defender for Cloud — Terraform Activation

HCL — modules/security/defender/main.tf

# Enable Microsoft Defender for Cloud across all required resource types locals { defender_plans = toset([ "VirtualMachines", "SqlServers", "AppServices", "StorageAccounts", "Containers", "KeyVaults", "Arm", "Dns", "OpenSourceRelationalDatabases" ]) } resource "azurerm_security_center_subscription_pricing" "plans" { for_each = local.defender_plans resource_type = each.value tier = "Standard" } resource "azurerm_security_center_workspace" "default" { scope = "/subscriptions/${var.subscription_id}" workspace_id = var.log_analytics_workspace_id } # Auto-provisioning of MMA/AMA agent resource "azurerm_security_center_auto_provisioning" "mma" { auto_provision = "On" } # Enable Defender for Cloud workflow automation — export alerts to Sentinel resource "azurerm_security_center_automation" "sentinel_export" { name = "export-to-sentinel" location = var.location resource_group_name = var.resource_group_name scopes = ["/subscriptions/${var.subscription_id}"] action { type = "LogicApp" resource_id = var.sentinel_logic_app_id connection_string = var.sentinel_logic_app_connection } source { event_source = "Alerts" rule_set_name = "default" rule { expected_value = "High" operator = "Contains" property_path = "properties.severity" property_type = "String" } } }

6.2  FinOps — Tag Compliance & Cost Reporting

PowerShell — P5-01-finops-tag-report.ps1

param( [string[]]$SubscriptionIds, [string[]]$RequiredTags = @('Environment','WorkloadName','CostCentre','Owner','MigrationWave'), [string]$OutputPath = 'finops-tag-compliance.csv' ) $report = @() foreach ($subId in $SubscriptionIds) { Set-AzContext -SubscriptionId $subId -ErrorAction Stop ¦ Out-Null $ $sub = Get-AzSubscription -SubscriptionId $subId $ $resources = Get-AzResource foreach ($res in $resources) { $ $tags = $res.Tags ?? @{} $ $missing = $RequiredTags ¦ Where-Object { -not $tags.ContainsKey($_) } $ $report += [PSCustomObject]@{ SubscriptionName = $sub.Name ResourceName = $res.Name ResourceType = $res.ResourceType ResourceGroup = $res.ResourceGroupName TagsPresent = ($RequiredTags ¦ Where-Object { $tags.ContainsKey($_) }) -join ', ' TagsMissing = $missing -join ', ' Compliant = ($missing.Count -eq 0) } } } $report ¦ Export-Csv $OutputPath -NoTypeInformation $compliant = ($report ¦ Where-Object Compliant).Count $total = $report.Count $pct = if ($total -gt 0) { [math]::Round($compliant/$total*100,1) } else { 0 } Write-Host "Tag compliance: $compliant/$total resources ($pct%)" -ForegroundColor $(if ($pct -ge 90) {"Green"} else {"Yellow"}) Write-Host "Report saved: $OutputPath"

FinOps Budget Alert — Terraform

HCL — modules/governance/finops/main.tf

# FinOps budget alerts per subscription — warning at 80%, critical at 100% resource "azurerm_consumption_budget_subscription" "workload" { for_each = var.subscription_budgets name = "budget-${each.key}-${var.environment}" subscription_id = each.value.subscription_id amount = each.value.monthly_budget_gbp time_grain = "Monthly" time_period { start_date = "${formatdate("YYYY-MM", timestamp())}-01" } notification { enabled = true threshold = 80 operator = "GreaterThan" threshold_type = "Actual" contact_emails = each.value.alert_emails } notification { enabled = true threshold = 100 operator = "GreaterThan" threshold_type = "Actual" contact_emails = each.value.alert_emails contact_groups = [var.ops_action_group_id] } } # Cost allocation tag inheritance policy resource "azurerm_management_group_policy_assignment" "tag_inheritance" { name = "inherit-cost-tags" management_group_id = var.management_group_id policy_definition_id = "/providers/Microsoft.Authorization/policyDefinitions/cd3aa116-8754-49c9-a813-ad46512ece54" parameters = jsonencode({ tagName = { value = "CostCentre" } }) }

6.3  Phase 5 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| Defender for Cloud — all plans enabled (Terraform) | modules/security/defender/ | Sec. Eng. | S3+ |
| FinOps tag compliance report (weekly) | P5-01-finops-tag-report.ps1 | Mig. Eng. | S6+ |
| Budget alerts per subscription (Terraform) | modules/governance/finops/ | Mig. Eng. | S6+ |
| Sentinel SIEM — analytic rules deployed (Terraform) | modules/security/sentinel/ | Sec. Eng. | S7+ |
| Secure Score baseline — documented and tracked | Azure Security Center API | Sec. Eng. | S6 |
| Key Vault per workload (Terraform) | modules/security/key-vault/ | Mig. Eng. | S7 |
| NSG flow logs enabled across all subnets | modules/networking/nsg-flow-logs/ | Mig. Eng. | S7 |

| PHASE 6 | Operate & Optimise SLO/SLI monitoring, DR pipelines, knowledge transfer, continuous optimisation |
| --- | --- |

7.1  SLO/SLI Framework — Azure Monitor Alerts via Terraform

HCL — modules/monitoring/slo-alerts/main.tf

# SLO/SLI alert rules per workload tier # Tier 1: 99.95% availability ¦ p99 latency < 200ms ¦ error rate < 0.1% resource "azurerm_monitor_scheduled_query_rules_alert" "availability_slo" { for_each = var.workloads name = "slo-availability-${each.key}" location = var.location resource_group_name = each.value.resource_group_name action { action_group = [var.ops_action_group_id] } data_source_id = var.log_analytics_workspace_id frequency = 5 # minutes time_window = 30 query = <<-KQL let sloTarget = ${each.value.availability_slo}; AppRequests ¦ where AppRoleName == '${each.key}' ¦ summarize total = count(), success = countif(Success == true) by bin(TimeGenerated, 5m) ¦ extend availability = todouble(success) / todouble(total) ¦ where availability < sloTarget KQL severity = each.value.tier <= 2 ? 1 : 2 description = "${each.key} availability below SLO target ${each.value.availability_slo * 100}%" trigger { operator = "GreaterThan", threshold = 0 } } resource "azurerm_monitor_scheduled_query_rules_alert" "error_budget_burn" { for_each = var.workloads name = "slo-errbudget-burn-${each.key}" location = var.location resource_group_name = each.value.resource_group_name action { action_group = [var.ops_action_group_id] } data_source_id = var.log_analytics_workspace_id frequency = 5 time_window = 60 query = <<-KQL // Fast burn: error budget burning 14x faster than allowed let errorBudgetPct = 1 - ${each.value.availability_slo}; let burnMultiple = 14.0; AppRequests ¦ where AppRoleName == '${each.key}' ¦ summarize total = count(), failed = countif(Success == false) by bin(TimeGenerated, 5m) ¦ extend errorRate = todouble(failed) / todouble(total) ¦ where errorRate > errorBudgetPct * burnMultiple KQL severity = 1 description = "${each.key} error budget burning at 14x — page immediately" trigger { operator = "GreaterThan", threshold = 0 } }

DR Automated Failover Test Pipeline

YAML — pipelines-templates/dr-test-pipeline.yml

# Automated DR failover test — scheduled quarterly # Tests ASR failover into isolated network, validates app, then fails back schedules: - cron: '0 2 1 */3 *' # 02:00 UTC on 1st day of every 3rd month displayName: Quarterly DR Test branches: { include: [main] } always: true parameters: - name: workloadName type: string - name: vaultName type: string - name: isolatedNetworkId type: string stages: - stage: PreDRChecks displayName: '1 — Pre-DR Validation' jobs: - job: checks pool: { vmImage: ubuntu-latest } steps: - task: AzurePowerShell@5 inputs: azureSubscription: $(SERVICE_CONNECTION) ScriptType: InlineScript Inline: ¦ $vault = Get-AzRecoveryServicesVault -Name '${{ parameters.vaultName }}' Set-AzRecoveryServicesVaultContext -Vault $vault $items = Get-AzRecoveryServicesAsrReplicationProtectedItem $unhealthy = $items ¦ Where-Object { $_.ReplicationHealth -ne 'Normal' } if ($unhealthy.Count -gt 0) { throw "Unhealthy replications: $($unhealthy.FriendlyName)" } Write-Host 'All replications healthy.' -ForegroundColor Green azurePowerShellVersion: LatestVersion - stage: TestFailover displayName: '2 — Test Failover (Isolated Network)' dependsOn: PreDRChecks jobs: - deployment: dr_test environment: dr-test pool: { vmImage: ubuntu-latest } strategy: runOnce: deploy: steps: - task: AzurePowerShell@5 inputs: azureSubscription: $(SERVICE_CONNECTION) ScriptType: InlineScript Inline: ¦ python dr_tests/run_dr_test.py \ --workload '${{ parameters.workloadName }}' \ --vault '${{ parameters.vaultName }}' \ --network '${{ parameters.isolatedNetworkId }}' azurePowerShellVersion: LatestVersion - stage: ValidateDR displayName: '3 — Validate App in DR' dependsOn: TestFailover jobs: - job: validate pool: { vmImage: ubuntu-latest } steps: - script: ¦ python smoke_tests/run_wave_smoke_tests.py \ --vms $(DR_VM_NAMES) \ --subscription $(ARM_SUBSCRIPTION_ID) displayName: 'Run smoke tests against DR VMs' - stage: Cleanup displayName: '4 — Cleanup Test Failover' dependsOn: ValidateDR condition: always() jobs: - job: cleanup pool: { vmImage: ubuntu-latest } steps: - task: AzurePowerShell@5 inputs: azureSubscription: $(SERVICE_CONNECTION) ScriptType: InlineScript Inline: ¦ $vault = Get-AzRecoveryServicesVault -Name '${{ parameters.vaultName }}' Set-AzRecoveryServicesVaultContext -Vault $vault Get-AzRecoveryServicesAsrReplicationProtectedItem ¦ Where-Object { $_.FailoverRecoveryPointId } ¦ ForEach-Object { Start-AzRecoveryServicesAsrTestFailoverCleanupJob -ReplicationProtectedItem $_ } Write-Host 'DR test VMs cleaned up.' -ForegroundColor Green azurePowerShellVersion: LatestVersion

7.2  Knowledge Transfer — Delivery Checklist

| KT Activity | Format | Sprint | Status |
| --- | --- | --- | --- |
| Terraform & IaC Fundamentals workshop (2-day hands-on) | Workshop + lab | S6 | ☐ |
| Azure DevOps Pipeline Patterns (1-day walkthrough) | Workshop | S6 | ☐ |
| Azure Policy & Governance (half-day + lab) | Workshop | S7 | ☐ |
| Migration Pattern Library — recorded demos | Recorded video + wiki | Ongoing | ☐ |
| Per-workload operational runbooks authored | Word doc per workload | S10–S12 | ☐ |
| SLO/SLI & Monitoring framework (half-day walkthrough) | Workshop + dashboards | S12 | ☐ |
| DR Failover Procedures — tabletop + live rehearsal | Tabletop + DR test | S12 | ☐ |
| FinOps & Cost Governance (half-day + Power BI walkthrough) | Workshop | S8 | ☐ |
| Wiki structure populated (all 8 sections) | Azure DevOps Wiki | S8–S12 | ☐ |
| Handover pack per wave (arch diagram, RACI, risks) | Word / PDF | S10–S13 | ☐ |
| Client engineers independently deploy module (witnessed) | Live exercise | S13 | ☐ |
| Programme retrospective & lessons learned | Workshop | S13 | ☐ |

7.3  Phase 6 Deliverables

| Deliverable | Automation / Script | Owner | Sprint |
| --- | --- | --- | --- |
| SLO/SLI alert rules per workload (Terraform) | modules/monitoring/slo-alerts/ | Mig. Eng. | S12+ |
| Azure Monitor dashboards per workload | ARM / Terraform dashboard resource | Mig. Eng. | S12+ |
| Automated DR test pipeline | pipelines-templates/dr-test-pipeline.yml | Mig. Eng. | S12 |
| Per-workload operational runbooks | Word doc per workload (wiki) | Mig. Eng. | S10–S12 |
| Handover packs all waves (signed off) | Word / PDF — per wave | Cloud Arch. | S13 |
| Full wiki (8 sections) complete | Azure DevOps Wiki | Mig. Eng. | S12 |
| Client team independently operate estate | Witnessed exercise — sign-off | Mig. Eng. | S13 |
| Programme retrospective report | Word doc | Cloud Arch. | S13 |

8.  Sprint Plan Summary — All Phases

The table below consolidates the full 13-sprint delivery plan. Each row represents one 2-week sprint with its primary focus, key deliverables, and pipeline gate requirements.

| Sprint | Phase | Focus | Key Deliverables | Pipeline Gate |
| --- | --- | --- | --- | --- |
| S1 | P1 | Discover | Appliance deployed, discovery running, credentials configured | Azure Migrate appliance health check |
| S2 | P1 | Assess | Inventory CSV, wave matrix, readiness report, wave plan | Wave plan ARB sign-off |
| S3 | P2 | Design | Repos + policies, TF backend, networking module v1.0.0 | Module CI pipeline green |
| S4 | P2 | Design | Identity module, MG hierarchy, DEV Landing Zone deployed | Policy compliance 100% |
| S5 | P2 | Design | QA + PROD Landing Zones, hub firewall live, DNS configured | Post-apply tests green |
| S6 | P3 | Build | CI/CD template, policy initiative, Defender enabled, FinOps | All pipeline stages green |
| S7 | P3 | Build | Post-apply tests, policy check script, tflint/tfsec configs | Security scan: 0 HIGH/CRITICAL |
| S8 | P3 | Build | terraform-docs CI, all module READMEs, KT workshops 1-2 | Module README review |
| S9 | P4 | Migrate | ASR vault, W1 pre-cutover test failover, cutover scripts | Smoke tests: 100% pass |
| S10 | P4 | Migrate | Wave 1 cutover + validation, runbooks authored | Wave 1 ARB sign-off |
| S11 | P4 | Migrate | Wave 2 cutover + validation, decommission plan | Wave 2 ARB sign-off |
| S12 | P4+P6 | Migrate+Operate | Wave 3 cutover, SLO alerts, DR pipeline, KT workshops 3-8 | SLO alerts firing correctly |
| S13 | P6 | Operate | Handover packs, client independence exercise, retrospective | Handover sign-off — all |

9.  Complete Script & Artefact Index

The table below is the canonical reference for every script, Terraform module, pipeline template, and test file produced during the programme. All artefacts are versioned in Azure Repos.

| Ref | File / Path | Type | Phase | Repo |
| --- | --- | --- | --- | --- |
| P1-01 | 00-bootstrap-toolchain.ps1 | PowerShell | Pre-programme | workstation |
| P1-02 | P1-01-deploy-migrate-appliance.ps1 | PowerShell | Phase 1 | migration-automation |
| P1-03 | P1-02-export-inventory.py | Python | Phase 1 | migration-automation |
| P1-04 | P1-03-enable-dependency-agents.ps1 | PowerShell | Phase 1 | migration-automation |
| P2-01 | P2-00-repo-init.sh | Bash | Phase 2 | migration-automation |
| P2-02 | P2-01-setup-tf-backend.ps1 | PowerShell | Phase 2 | infra-landing-zone |
| P2-03 | modules/networking/hub-spoke/ | Terraform | Phase 2 | infra-migration-patterns |
| P2-04 | modules/identity/rbac-baseline/ | Terraform | Phase 2 | infra-migration-patterns |
| P2-05 | modules/governance/management-groups/ | Terraform | Phase 2 | infra-migration-patterns |
| P3-01 | pipelines-templates/terraform-cicd.yml | Azure DevOps YAML | Phase 3 | pipelines-templates |
| P3-02 | modules/governance/policy-initiative/ | Terraform | Phase 3 | migration-governance |
| P3-03 | migration-automation/tests/post_apply_validate.py | Python | Phase 3 | migration-automation |
| P3-04 | migration-automation/tests/policy_compliance_check.py | Python | Phase 3 | migration-automation |
| P4-01 | modules/migration/asr-replication/ | Terraform | Phase 4 | infra-migration-patterns |
| P4-02 | P4-01-wave-cutover.ps1 | PowerShell | Phase 4 | migration-automation |
| P4-03 | smoke_tests/run_wave_smoke_tests.py | Python | Phase 4 | migration-automation |
| P4-04 | P4-02-rollback-failback.ps1 | PowerShell | Phase 4 | migration-automation |
| P5-01 | modules/security/defender/ | Terraform | Phase 5 | migration-governance |
| P5-02 | P5-01-finops-tag-report.ps1 | PowerShell | Phase 5 | migration-automation |
| P5-03 | modules/governance/finops/ | Terraform | Phase 5 | migration-governance |
| P6-01 | modules/monitoring/slo-alerts/ | Terraform | Phase 6 | infra-migration-patterns |
| P6-02 | pipelines-templates/dr-test-pipeline.yml | Azure DevOps YAML | Phase 6 | pipelines-templates |